## Main Fixes
Main Defects Addressed in this Release
Attribute name change: Old Attribute Name New Attribute Name Hispanic_or_Latino Ethnicity Ethnicity Race_Multiple_Allowed Race Race_and_Ethnicity
Incremental change logic has issues when changes were made to position, cost center and academic appointment. This defect was identified during cycle 1 and cycle 2 testing.
Terminated records were missing from final view. This issue is fixed.
SRT Hist Finding cost center from home org for people who are missing cost center. This is done we now have only 4 Upi's missing cost centers. This is because their identity is not in IDR.
Job_Category_Grouping was missing for future worked. This issue is fixed.
Grouper data was not showing changes after daily load. This is addresses.
Data records that are deleted in source will be endated in people Hub.

## ALM Defects
Defect ID | Detected By | Status | Summary
4178 | ghl8 | Closed | Deleted in source
4239 | sl2393 | Closed | Future Worker and Futute Position
4730 | sl2393 | Closed | Add to DQ Error Checks
4904 | sl2393 | Closed | worker is both a "Retired Employee" and "Active Contingent Worker"
4946 | er92 | Ready for Retest | ExtractAdhocPopulationGroups is not updated on daily load
4956 | am2947 | Closed | Update DV Data Quality checks to use cycle date
4962 | ap349 | Closed | Update DV Data Quality checks to use cycle date
5011 | sl2393 | Closed | UPdate term date logic for SQN
5021 | sl2393 | Closed | delimiter consistancy
5051 | sl2393 | Closed | Duplicate records inVisibleHistoricalUpiForPrincipal_Rset_B
5052 | er92 | Ready for Retest | mail stop missing for VF, other mail stop attributes populated
5055 | sl2393 | Closed | Schedulle table needs to be updated over the weekend
5087 | sl2393 | Closed | Effectivity SAT for Link_Person_Academic_Appointment
5107 | am2947 | Closed | Sat_Education change detection
5124 | mr2274 | Closed | Data check error messages
5127 | sl2393 | Closed | Mapping_Cost_Center_Hist_B
5129 | er92 | Ready for Retest | find job_category_grouping NULL for 'active' workers
5131 | er92 | Ready for Retest | Expect all active workers to have non-null age_group
5132 | er92 | Ready for Retest | expect all active workers to have non-null cost center
5135 | sl2393 | Closed | Key different in STG_IDR_All_Identities_V and Hub_Supervisory_Org:
5139 | sl2393 | Closed | Create Taland TEST code repository project
5142 | ls47 | Ready for Retest | PHUB Test Case 22 - PH Columns Null
5148 | sl2393 | Closed | When employees position business keys change
5151 | er92 | Ready for Retest | Mail_stop and associated attributes not null, zip_code is null
5152 | er92 | Ready for Retest | Work_address data issues
5165 | sl2393 | Closed | Database transaction log full, cycle fails at start when copy BtoA runs
5172 | sl2393 | Closed | New sat needed for this Links
5178 | cv233 | Ready for Retest | Academic_Unit_Inactive = Null
5191 | cv233 | Ready for Retest | Full_Name is not formatting correctly in most instances
5192 | cv233 | Ready for Retest | Field Name and Field Formatting
5193 | mr2274 | Closed | Error messages in Data check error table
5194 | sl2393 | Closed | Sats with Mulit-part key , Sat_Education need special end-date logic
5196 | mr2274 | Closed | Data check error messages
5199 | sl2393 | Closed | End date sat sat_address_WD
5201 | mr2274 | Closed | Future Worker missing in PeopleHub View
5206 | mw629 | Closed | ISSUES WITH 3/20 Release Data
5214 | mr2274 | Closed | Incorrect Worker Status
5215 | sl2393 | Closed | Matrix Manager and '' entries
5218 | mr2274 | Closed | Person moving from Employee to Student - Identity Issue
5220 | jfo4 | Ready for Retest | Library Voyager People Hub - Missing EduPersonAffiliation
5224 | er92 | Ready for Retest | Sponsored guest ID is not null, other sponsored_identity attributes are null
5227 | desalvmj | Closed | PeopleHub LimitedPeopleService Failing
5229 | se367 | Ready for Retest | Mismatch SSN between Yale 2 and PeopleHub
5230 | se367 | Ready for Retest | Mismatch Emp ID between Yale 2 and PeopleHub
5232 | mr2274 | Closed | Legacy_Job_Category is NULL
5237 | sl2393 | Closed | Implement next gen Sat/Stage insert where condition
5238 | se367 | Ready for Retest | Home and Work Address, Sup Orgs and Work Email
5239 | desalvmj | Ready for Retest | People missing from PeopleHub
5241 | er92 | Ready for Retest | 2 test cases have null age_group
5244 | sl2393 | Closed | IDR missing Yale Relationship for some UPI
5245 | sl2393 | Closed | Create Taland TEST code repository project
5249 | mr2274 | Closed | Identity Issue
5252 | er92 | Ready for Retest | Test case #22 incorrect
5255 | jfo4 | Closed | People Hub Cost Center Missing Hierarchy Information for one Cost Center
5256 | sa553 | Closed | YLS:Inside and People Hub ... Can Law School depend on the PH Load Status table to know that the overnight load is completed?
5261 | er92 | Closed | UPI = '17216750' missing
5262 | sl2393 | Closed | Sat_Person_Affiliations_IDR
5263 | jfo4 | Ready for Retest | Library Voyager People Hub - Faculty member showing as SI in Yale Relationship
5266 | sl2393 | Closed | [dbo].[STG_WD_1192_Worker_V]
5267 | sl2393 | Closed | Future worker in both services
5268 | sl2393 | Closed | Mapping is wrong for Education degree and Degree Discription
5278 | jfo4 | Ready for Retest | EHS People Hub .... remove records no longer needed
5279 | er92 | Ready for Retest | Data available in GROUPER TEST is not available in People Hub to 2 service accounts
5280 | jfo4 | Ready for Retest | People Hub Race and Ethnicity ... Revised Language
5289 | mr2274 | Closed | Incorrect Job category grouping
5290 | mr2274 | Closed | Incorrect Job category grouping
5295 | mr2274 | Closed | Incorrect Job category grouping
5322 | mr2274 | Closed | Incorrect Job category grouping
5344 | mr2274 | Closed | Incorret job category and job category grouping
5348 | mr2274 | Closed | Incorrect Primary Yale relationship
5355 | mr2274 | Closed | Incorrect Job category grouping
5359 | mr2274 | Closed | Identity Issue
5361 | mr2274 | Closed | Mismatch in Mailstop
5365 | mr2274 | Closed | Incorrect Job Category Grouping
5366 | mr2274 | Closed | Incorrect Job Category grouping and worker status